## Slide 1
Meeting 07/09/2020
Shuo Zhang

## Slide 2: In past week
1) PPO for real hand: Done
2) Clean and wrapped codes so far + managed experiment's logistic: Done
3) 10 rollouts for A* and PPO on reacher and acrobot: Done
4) 10 rollouts for gazebo: Done (on my own machine, 14 hours)
5) Got all statistics: Done
6) Write rollout ros package codes for real hand: Just to start

## Slide 3
Progress
 | A* Plan + Rollout + Statistic | PPO Plan + Rollout + Statistic | Online Method
Acrobot | Done | Done | Need to discuss in more details
Reacher | Done | Done | Need to discuss in more details
Gazebo Hand (normal obstacles + horseshoe ) | Done | Done | Need to discuss in more details
Real Had (no obstacles) | Plan is done. (Wait for Mridul until the marker issues fixed) | Plan is done. (Wait for Mridul until the marker issues fixed) | Need to discuss in more details

## Slide 4
goal location (method) | success rollout rate | goal reach rate | success rollout path RMSE relative to plan path [mm] | path length [mm] |  |  | number of path steps |  | last distance to goal [mm] |  | 
 |  |  |  | plan | success rollout | failure | plan | failure | plan | success rollout | failure
0 (A*) | 0% | 0% | - | 75.88 | - | 75.35±5.94 | 390 | 375.8±31.3 | 5.50 | - | 11.43±4.29
0 (policy) | 100% | 100% | 1.80±0.02 | 150.18 | 98.68±0.76 | - | 947 | - | 5.49 | 5.13±0.22 | -
2 (A*) | 100% | 100% | 1.26±0.06 | 63.10 | 62.79±0.11 | - | 295 | - | 5.38 | 4.89±0.10 | -
2 (policy) | 100% | 100% | 1.08±0.06 | 77.14 | 62.90±0.04 | - | 385 | - | 5.49 | 4.70±0.11 | -
7 (A*) | 100% | 100% | 0.79±0.03 | 59.08 | 58.73±0.11 | - | 197 | - | 5.49 | 5.20±0.09 | -
7 (policy) | 60% | 50% | 1.45±0.05 | 110.43 | 59.82±0.38 | 9.06±0.06 | 695 | 109.25±0.43 | 5.36 | 7.84±0.12 | 54.14±0.05
8 (A*) | 100% | 100% | 0.94±0.01 | 58.04 | 57.68±0.07 | - | 289 | - | 5.50 | 5.63±0.06 | -
8 (policy) | 40% | 40% | 1.39±0.04 | 109.89 | 59.82±0.19 | 8.90±0.12 | 752 | 94±0.57 | 5.47 | 7.22±0.37 | 48.74±0.09
15 (A*) | 100% | 100% | 1.01±0.01 | 80.85 | 80.71±0.14 | - | 436 | - | 5.46 | 6.08±0.16 | -
15 (policy) | 20% | 0% | 3.66±0.04 | 191.42 | 104.59±0.06 | 8.96±0.11 | 1299 | 90±1.87 | 5.41 | 9.35±0.32 | 72.10±0.08
horseshoe (A*) | 90% | 90% | 3.87±0.04 | 165.17 | 173.71±0.47 | 162.05±0 | 731 | 680±0 | 3.37 | 3.00±0.30 | 9.53±0
horseshoe (policy) | - | - | - | - | - | - | - | - | - | - | -
Gazebo Hand Statistics

## Slide 5
A*
Policy

## Slide 6
goal location (method) | goal reach rate | rollout path RMSE relative to plan path [mm] | path length [mm] |  | number of path steps | last distance to goal [mm] | 
 |  |  | plan | rollout |  | plan | rollout
1 (A*) | 100% | 0.01025±0.00091 | 0.22799 | 0.24568±0.00221 | 16 | 0.00778 | 0.00993±0.00112
1 (policy) | 60% | 0.00599±0.00203 | 0.87181 | 0.86061±0.00931 | 51 | 0.03055 | 0.02295±0.00937
2 (A*) | 100% | 0.0034±0.00065 | 0.24392 | 0.24707±0.00159 | 26 | 0.00859 | 0.00509±0.00105
2 (policy) | 0% | 0.01801±.00191 | 0.72881 | 0.78558±0.01989 | 51 | 0.06385 | 0.04545±0.00596
5 (A*) | 100% | 0.00871±0.00373 | 0.31887 | 0.32344±0.00551 | 23 | 0.00449 | 0.00598±0.00154
5 (policy) | 0% | 0.01307±0.00383 | 1.05959 | 1.00686±0.01665 | 51 | 0.06024 | 0.05161±0.00201
Reacher-v2 Statistics

## Slide 7
A*
Policy

## Slide 8
goal location (method) | goal reach rate | rollout path RMSE relative to plan path [mm] | path length [mm] |  | number of path steps |  | last distance to goal [mm] | 
 |  |  | plan | rollout | plan | rollout | plan | rollout
1 (A*) | 60% | 0.77±0.09 | 104.91 | 94.52±28.19 | 419 | 331.3±85.19 | 0.97 | 1.00±1.24
1 (policy) | 30% | 0.61±0.11 | 17.83 | 23.13±6.92 | 104 | 94.9±14.26 | 0 | 1.10±0.98
Acrobot-v1 Statistics
A*
Policy

## Slide 9
Real Hand Plan
Policy
A*

## Slide 10
To Do List
Writing a ros-package for rollouts of the Real Hand.
(Avishai’s previous rollout ros-package only works on the Motoman setup)
Work on our new online method
Real Hand
Test whether the trained real hand dynamics model also works with Mridul’s new data or not
Do rollouts for A* and PPO policy on real hand
Mridul:
- Fix the issues of marker tracking
- Collect several episodes of data for testing my trained dynamics model